## Orçamento
OBRA: |  |  | ESCADÕES RUA TABATA E TELMA - PQ WEY
Tipo de Intervenção: |  |  | CONSTRUÇÃO
Endereço : |  |  | Rua Tabata, – Parque Wey, Itapevi/SP Rua Telma, – Parque Wey, Itapevi/SP |  | Investimento: |  | 0
TAB. REF.: |  |  | SIURB INFRA- JAN/23; SINAPI - MAI/23 / CDHU - 190, FDE ABR/23
Item | Ref. | Código | Descrição dos Serviços | Un. | Qtd. | Custo un. | Custo Total | %
1 |  |  | SERVIÇOS PRELIMINARES | 0 |  |  |  | #DIV/0!
01.01 |  |  | SERVIÇOS PRELIMINARES | 0 |  |  |  | #DIV/0!
01.01.01 | SIURB INFRA | 101603 | PLACA DE OBRA EM CHAPA DE AÇO GALVANIZADO | M2 | 6 |  | 0 | #DIV/0!
01.01.02 | FDE | 16.80.097 | CAÇAMBA DE 4M3 PARA RETIRADA DE ENTULHO | UN | 4 |  | 0 | #DIV/0!
2 |  |  | ESCADÃO RUA TAMARA/RUA TELMA | 0 |  |  |  | #DIV/0!
02.01 |  |  | MOVIMENTAÇÃO DE TERRA E LIMPEZA DO TERRENO | 0 |  |  |  | #DIV/0!
02.01.01 | CDHU | 02.09.030 | Limpeza manual do terreno, inclusive troncos até 5 cm de diâmetro, com caminhão à disposição dentro da obra, até o raio de 1 km | M2 | 490 |  | 0 | #DIV/0!
02.01.02 | SINAPI | 93358 | ESCAVAÇÃO MANUAL DE VALA COM PROFUNDIDADE MENOR OU IGUAL A 1,30 M. AF_02/2021 | M3 | 205 |  | 0 | #DIV/0!
02.01.03 | SINAPI | 93382 | REATERRO MANUAL DE VALAS COM COMPACTAÇÃO MECANIZADA. AF_04/2016 | M3 | 123 |  | 0 | #DIV/0!
02.01.04 | CDHU | 06.14.020 | Carga manual de solo | M3 | 82 |  | 0 | #DIV/0!
02.01.05 | SINAPI | 95875 | TRANSPORTE COM CAMINHÃO BASCULANTE DE 10 M³, EM VIA URBANA PAVIMENTADA, DMT ATÉ 30 KM (UNIDADE: M3XKM). AF_07/2020 | M3XKM | 492 |  | 0 | #DIV/0!
02.01.06 | CDHU | 05.09.007 | Taxa de destinação de resíduo sólido em aterro, tipo solo/terra | M3 | 82 |  | 0 | #DIV/0!
02.02 |  |  | ESTRUTURA | 0 |  |  |  | #DIV/0!
02.02.01 | CDHU | 11.18.040 | Lastro de pedra britada | M3 | 14 |  | 0 | #DIV/0!
02.02.02 | CDHU | 11.18.060 | Lona plástica - 150 micron | M2 | 144 |  | 0 | #DIV/0!
02.02.03 | CDHU | 12.01.041 | Broca em concreto armado diâmetro de 25 cm - completa | M | 176 |  | 0 | #DIV/0!
02.02.04 | SINAPI | 103686 | CONCRETAGEM DE ESCADAS, FCK=25 MPA, COM USO DE BOMBA - LANÇAMENTO, ADENSAMENTO E ACABAMENTO. AF_02/2022_PS | M3 | 37 |  | 0 | #DIV/0!
02.02.05 | SINAPI | 95945 | ARMAÇÃO DE ESCADA, DE UMA ESTRUTURA CONVENCIONAL DE CONCRETO ARMADO UTILIZANDO AÇO CA-50 DE 8,0 MM - MONTAGEM. AF_11/2020 | KG | 1220 |  | 0 | #DIV/0!
02.02.06 | CDHU | 10.01.040 | Armadura em barra de aço CA-50 (A ou B) fyk = 500 MPa | KG | 1152 |  | 0 | #DIV/0!
02.02.07 | CDHU | 09.01.030 | Forma em madeira comum para estrutura | M2 | 94 |  | 0 | #DIV/0!
02.03 |  |  | ALVENARIA | 0 |  |  |  | #DIV/0!
02.03.01 | CDHU | 14.10.121 | Alvenaria de bloco de concreto de vedação de 19 x 19 x 39 cm - classe C | M2 | 188 |  | 0 | #DIV/0!
02.03.02 | CDHU | 17.02.020 | Chapisco | M2 | 404.8 |  | 0 | #DIV/0!
02.03.03 | CDHU | 17.02.120 | Emboço comum | M2 | 404.8 |  | 0 | #DIV/0!
02.03.04 | CDHU | 17.02.220 | Reboco | M2 | 404.8 |  | 0 | #DIV/0!
02.03.05 | SINAPI | 93205 | CINTA DE AMARRAÇÃO DE ALVENARIA MOLDADA IN LOCO COM UTILIZAÇÃO DE BLOCOS CANALETA. AF_03/2016 | M | 144 |  | 0 | #DIV/0!
02.04 |  |  | DIVERSOS | 0 |  |  |  | #DIV/0!
02.04.01 | SIURB EDIF | 130247 | PISO PODOTÁTIL, ALERTA OU DIRECIONAL, EM LADRILHO HIDRÁULICO | M2 | 9.6 |  | 0 | #DIV/0!
02.04.02 | CDHU | 24.03.310 | Corrimão tubular em aço galvanizado, diâmetro 1 1/2´ | M | 288 |  | 0 | #DIV/0!
02.05 |  |  | PINTURA | 0 |  |  |  | #DIV/0!
02.05.01 | CDHU | 33.10.041 | Esmalte à base de água em massa, inclusive preparo | M2 | 50 |  | 0 | #DIV/0!
02.05.02 | CDHU | 33.10.050 | Tinta acrílica em massa, inclusive preparo | M2 | 404.8 |  | 0 | #DIV/0!
3 |  |  | ESCADÃO RUA TELMA/RUA TABATA | 0 |  |  |  | #DIV/0!
03.01 |  |  | MOVIMENTAÇÃO DE TERRA E LIMPEZA DO TERRENO | 0 |  |  |  | #DIV/0!
03.01.01 | CDHU | 02.09.030 | Limpeza manual do terreno, inclusive troncos até 5 cm de diâmetro, com caminhão à disposição dentro da obra, até o raio de 1 km | M2 | 190 |  | 0 | #DIV/0!
03.01.02 | SINAPI | 93358 | ESCAVAÇÃO MANUAL DE VALA COM PROFUNDIDADE MENOR OU IGUAL A 1,30 M. AF_02/2021 | M3 | 60 |  | 0 | #DIV/0!
03.01.03 | SINAPI | 93382 | REATERRO MANUAL DE VALAS COM COMPACTAÇÃO MECANIZADA. AF_04/2016 | M3 | 30 |  | 0 | #DIV/0!
03.01.04 | CDHU | 06.14.020 | Carga manual de solo | M3 | 30 |  | 0 | #DIV/0!
03.01.05 | SINAPI | 95875 | TRANSPORTE COM CAMINHÃO BASCULANTE DE 10 M³, EM VIA URBANA PAVIMENTADA, DMT ATÉ 30 KM (UNIDADE: M3XKM). AF_07/2020 | M3XKM | 180 |  | 0 | #DIV/0!
03.01.06 | CDHU | 05.09.007 | Taxa de destinação de resíduo sólido em aterro, tipo solo/terra | M3 | 30 |  | 0 | #DIV/0!
03.02 |  |  | ESTRUTURA | 0 |  |  |  | #DIV/0!
03.02.01 | CDHU | 11.18.040 | Lastro de pedra britada | M3 | 5 |  | 0 | #DIV/0!
03.02.02 | CDHU | 11.18.060 | Lona plástica - 150 micron | M2 | 120 |  | 0 | #DIV/0!
03.02.03 | CDHU | 12.01.041 | Broca em concreto armado diâmetro de 25 cm - completa | M | 138 |  | 0 | #DIV/0!
03.02.04 | SINAPI | 103686 | CONCRETAGEM DE ESCADAS, FCK=25 MPA, COM USO DE BOMBA - LANÇAMENTO, ADENSAMENTO E ACABAMENTO. AF_02/2022_PS | M3 | 30 |  | 0 | #DIV/0!
03.02.05 | SINAPI | 95945 | ARMAÇÃO DE ESCADA, DE UMA ESTRUTURA CONVENCIONAL DE CONCRETO ARMADO UTILIZANDO AÇO CA-50 DE 8,0 MM - MONTAGEM. AF_11/2020 | KG | 1020 |  | 0 | #DIV/0!
03.02.06 | CDHU | 10.01.040 | Armadura em barra de aço CA-50 (A ou B) fyk = 500 MPa | KG | 960 |  | 0 | #DIV/0!
03.02.07 | CDHU | 09.01.030 | Forma em madeira comum para estrutura | M2 | 53 |  | 0 | #DIV/0!
03.03 |  |  | ALVENARIA | 0 |  |  |  | #DIV/0!
03.03.01 | CDHU | 14.10.121 | Alvenaria de bloco de concreto de vedação de 19 x 19 x 39 cm - classe C | M2 | 156 |  | 0 | #DIV/0!
03.03.02 | CDHU | 17.02.020 | Chapisco | M2 | 336 |  | 0 | #DIV/0!
03.03.03 | CDHU | 17.02.120 | Emboço comum | M2 | 336 |  | 0 | #DIV/0!
03.03.04 | CDHU | 17.02.220 | Reboco | M2 | 336 |  | 0 | #DIV/0!
03.03.05 | SINAPI | 93205 | CINTA DE AMARRAÇÃO DE ALVENARIA MOLDADA IN LOCO COM UTILIZAÇÃO DE BLOCOS CANALETA. AF_03/2016 | M | 120 |  | 0 | #DIV/0!
03.04 |  |  | DIVERSOS | 0 |  |  |  | #DIV/0!
03.04.01 | SIURB EDIF | 130247 | PISO PODOTÁTIL, ALERTA OU DIRECIONAL, EM LADRILHO HIDRÁULICO | M2 | 6 |  | 0 | #DIV/0!
03.04.02 | CDHU | 24.03.310 | Corrimão tubular em aço galvanizado, diâmetro 1 1/2´ | M | 240 |  | 0 | #DIV/0!
03.05 |  |  | PINTURA | 0 |  |  |  | #DIV/0!
03.05.01 | CDHU | 33.10.041 | Esmalte à base de água em massa, inclusive preparo | M2 | 43 |  | 0 | #DIV/0!
03.05.02 | CDHU | 33.10.050 | Tinta acrílica em massa, inclusive preparo | M2 | 336 |  | 0 | #DIV/0!
TOTAL GERAL | [5 empty] | 0 |  | #DIV/0!
TOTAL GERAL COM BDI | [5 empty] | 0 |  | #DIV/0!

## Resumo
OBRA: | ESCADÕES RUA TABATA E TELMA - PQ WEY
Tipo de Intervenção: CONSTRUÇÃO
Endereço : | Rua Tabata, – Parque Wey, Itapevi/SP Rua Telma, – Parque Wey, Itapevi/SP |  | Investimento: | 0
TAB. REF.: | SIURB INFRA- JAN/23; SINAPI - MAI/23 / CDHU - 190, FDE ABR/23
ITEM | DESCRIÇÃO DOS SERVIÇOS | VALOR TOTAL (sem BDI) | VALOR TOTAL (com BDI) | %
1 | SERVIÇOS PRELIMINARES | 0 | 0 | #DIV/0!
2 | ESCADÃO RUA TAMARA/RUA TELMA | 0 | 0 | #DIV/0!
3 | ESCADÃO RUA TELMA/RUA TABATA | 0 | 0 | #DIV/0!
TOTAL GERAL |  | 0 | 0 | #DIV/0!

## Cronograma Mensal
OBRA: | ESCADÕES RUA TABATA E TELMA - PQ WEY
Tipo de Intervenção: CONSTRUÇÃO |  |  |  | Investimento: |  |  | 0
Endereço : | Rua Tabata, – Parque Wey, Itapevi/SP Rua Telma, – Parque Wey, Itapevi/SP
Item | Descrição | Peso | Valor do Serviço | 1 | 2 | 3 | 4 | 11 | 12 | 13 | 14 | 15 | 16 | 17
|  | % | R$
1 | SERVIÇOS PRELIMINARES | #DIV/0! | 0 | 100% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | ESCADÃO RUA TAMARA/RUA TELMA | #DIV/0! | 0 | 50% | 50% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | ESCADÃO RUA TELMA/RUA TABATA | #DIV/0! | 0 |  |  | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub-Total | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Geral | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 7352306.3946 | 7352306.3946 | 7352306.3946 | 7352306.3946 | 7352306.3946 | 7352306.3946 | 7352306.3946

## Curva ABC
ITEM (CÓDIGO) | QUANTIDADE | CUSTO UNITÁRIO | VALOR TOTAL | PORCENTAGEM INDIVIDUAL | PORCENTAGEM ACUMULADA | CLASSIFICAÇÃO | DESCRIÇÃO | CLASSE | CORTE | PROPORÇÃO DE ITENS | PROPORÇÃO DE VALORES
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | A | 70% | #DIV/0! | 0%
16.80.097 | 4 | 0 | 0 | #REF! | #REF! |  | CAÇAMBA DE 4M3 PARA RETIRADA DE ENTULHO | B | 95% | #DIV/0! | 0%
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | C | 100% | #DIV/0! | 0%
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
33.10.050 | 404.8 | 0 | 0 | #REF! | #REF! |  | Tinta acrílica em massa, inclusive preparo
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
24.03.310 | 240 | 0 | 0 | #REF! | #REF! |  | Corrimão tubular em aço galvanizado, diâmetro 1 1/2´
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
33.10.050 | 336 | 0 | 0 | #REF! | #REF! |  | Tinta acrílica em massa, inclusive preparo
0 | 0 | 0 | 0 | #REF! | #REF! |  | PINTURA
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
06.14.020 | 82 | 0 | 0 | #REF! | #REF! |  | Carga manual de solo
05.09.007 | 82 | 0 | 0 | #REF! | #REF! |  | Taxa de destinação de resíduo sólido em aterro, tipo solo/terra
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
0 | 0 | 0 | 0 | #REF! | #REF! |  | MOVIMENTAÇÃO DE TERRA E LIMPEZA DO TERRENO
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
02.09.030 | 490 | 0 | 0 | #REF! | #REF! |  | Limpeza manual do terreno, inclusive troncos até 5 cm de diâmetro, com caminhão à disposição dentro da obra, até o raio de 1 km
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
33.10.041 | 43 | 0 | 0 | #REF! | #REF! |  | Esmalte à base de água em massa, inclusive preparo
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
95875 | 492 | 0 | 0 | #REF! | #REF! |  | TRANSPORTE COM CAMINHÃO BASCULANTE DE 10 M³, EM VIA URBANA PAVIMENTADA, DMT ATÉ 30 KM (UNIDADE: M3XKM). AF_07/2020
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
33.10.041 | 50 | 0 | 0 | #REF! | #REF! |  | Esmalte à base de água em massa, inclusive preparo
93382 | 123 | 0 | 0 | #REF! | #REF! |  | REATERRO MANUAL DE VALAS COM COMPACTAÇÃO MECANIZADA. AF_04/2016
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
93358 | 205 | 0 | 0 | #REF! | #REF! |  | ESCAVAÇÃO MANUAL DE VALA COM PROFUNDIDADE MENOR OU IGUAL A 1,30 M. AF_02/2021
130247 | 6 | 0 | 0 | #REF! | #REF! |  | PISO PODOTÁTIL, ALERTA OU DIRECIONAL, EM LADRILHO HIDRÁULICO
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
0 | 0 | 0 | 0 | #REF! | #REF! |  | ALVENARIA
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
11.18.040 | 14 | 0 | 0 | #REF! | #REF! |  | Lastro de pedra britada
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
0 | 0 | 0 | #REF! |  |  |  | ESCADÃO RUA TAMARA/RUA TELMA
0 | 0 | 0 | 0 |  |  |  | ESTRUTURA
0 | 0 | 0 | 0 |  |  |  | ESCADÃO RUA TELMA/RUA TABATA
0 | 0 | 0 | 0 |  |  |  | MOVIMENTAÇÃO DE TERRA E LIMPEZA DO TERRENO
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!
#REF! | #REF! | #REF! | #REF! |  |  |  | #REF!